## Slide 1: Project Management
Instructor: Mehroze Khan

## Slide 2: Project Planning
Before starting
  Establish system’s scope and objectives
  Consider alternative solutions
  Identify technical and management constraints
As a Project Manager
  Decompose the product function (FD)
  Select an appropriate process model
  Select the task set for the project
  Decompose the tasks into smaller work items (WBS)
  Estimate effort for each task/work item
  Estimate completion time of the project (Task/Activity Network)

## Slide 3: Task Set
A task set is a collection of software engineering work tasks, milestones, work products, and quality assurance filters that must be accomplished to complete a particular project.
To develop a project schedule, a task set must be distributed on the project timeline.

## Slide 4: Factors Affecting Choice of Task Set
Size of project
Number of potential users
Mission criticality
Application longevity
Stability of requirements
Ease of communication (customer/developer)
Maturity of applicable technology
Performance constraints
Embedded/Non-Embedded characteristics of project
Project Staff
Reengineering factors

## Slide 5: WBS and Activity Networks
Work breakdown structure depicts the project as a set of discrete pieces of work
Activity networks (task network, PERT [program evaluation and review technique] charts) depict the dependencies among activities
Activity networks can be of two types:
  Activity on Arc
  Activity on Node

## Slide 6: Project Types
Concept Development
  To explore new business concept
New Application Development
  As a consequence of specific customer request
Application Enhancement
  Modifications to existing functions, performance, interfaces of software; observable by the end user
Application Maintenance
  Correct, adapt, extend existing software; not immediately obvious to end user
Reengineering Projects
  Redevelop an existing system

## Slide 7: Concept Development Projects (CDP)
Usually initiated to explore some new business concept or application of some new technology
Task set might be like:
  1.1 Concept scoping determines the overall scope of the project.
  1.2 Preliminary concept planning establishes the organization’s ability to undertake
  the work implied by the project scope.
  1.3 Technology risk assessment evaluates the risk associated with the technology
  to be implemented as part of the project scope.
  1.4 Proof of concept demonstrates the viability of a new technology in the software
  context.
  1.5 Concept implementation implements the concept representation in a manner
  that can be reviewed by a customer and is used for “marketing” purposes
  when a concept must be sold to other customers or management.
  1.6 Customer reaction to the concept solicits feedback on a new technology concept
  and targets specific customer applications.

## Slide 8: Refinement of Major Tasks
Macroscopic schedule must be refined to create a detailed project schedule.
Refinement begins by taking each major task and decomposing it into a set of subtasks (with related work products and milestones).

## Slide 9: Refinement of Major Tasks (WBS of CDP)

## Slide 10: Activity Network
A task network, also called an activity network, is a graphic representation of the task flow for a project.
The task network is a useful mechanism for depicting inter task dependencies and determining the critical path.

## Slide 11: Activity Network of CDP
5
13
10
7
3
15
8
5
10
5
10
Activity on Node (AoN) Graph

## Slide 12: Critical Path Method
Analyzing the paths among the milestones of a project is called the Critical Path Method (CPM).
The paths can show us the minimum amount of time it will take to complete the project, given our estimates of each activity’s duration.
CPM reveals those activities that are most critical to completing the project on time.
Estimating Completion Critical Path Method

## Slide 13: Estimating Completion Critical Path Method
The real time or actual time for an activity is the estimated amount of time required for the activity to be completed.
The available time is the amount of time available in the schedule for the activity’s completion.
Slack time or float for an activity is the difference between the available time and the real time for that activity:
Slack time = available time - real time
Another way of looking at slack time is to compare the earliest time an activity may begin with the latest time the activity may begin without delaying the project.
Slack time = latest start time - earliest start time

## Slide 14: Estimating Completion Critical Path Method
The path that determines whether or not the project is on schedule. is called the critical path.
Thus, the critical path is the one for which the slack at every node is zero.

## Slide 15: Estimating Completion Critical Path Method
Critical path: the slack at every activity is zero
  can be more than one in a project schedule
Slack time =
  available time – real time
  latest start time – earliest start time
Paths????
Longest Path???

## Slide 16: Exercise
Activity | Predecessor | Duration (Days)
A | - | 20
B | A | 30
C | B, H | 10
D | A | 30
E | H | 20
F | C, D, E | 40
G | A | 40
H | G | 10

## Slide 17: Exercise
ES | ST | EF
Activity |  | 
LS | Dur | LF

## Slide 18: Exercise
Critical Path: A -> G -> H -> E -> F
60
20
0
20
20
50
30
20
80
50
0
60
60
20
70
0
60
0
70
40
50
20
90
60
10
90
70
80
80
0
90
70
90
70
0
130
90
130
90
0

## Slide 19: Exercise

## Slide 20: Exercise

## Slide 21: Timeline/Gantt Charts

## Slide 22: Project Table

## Slide 23: References
Shari PFleeger, Joanne Atlee, Software Engineering: Theory and Practice, 4th Edition
Roger S. Pressman, Software Engineering A Practitioner’s Approach, 9th Edition. McGrawHill