## Slide 1: Planning and Managing the Project: Effort Estimation
Instructor: Mehroze Khan

## Slide 2: Effort Estimation
Estimating project costs is one of the crucial aspects of project planning and management
Estimating cost must be done as early as possible during the project life cycle
Type of costs
  facilities: hardware, space, furniture, telephone, etc
  software tools for designing software
  staff (effort): the biggest component of cost

## Slide 3: Software Project Estimation
Software cost and effort estimation will never be an exact science
  Too many variables
    Human
    Technical
    Environmental
    Political

## Slide 4: Effort Estimation Estimation Should be Done Repeatedly
Uncertainty early in the project can affect the accuracy of cost and size estimations
Notes: The stars represent size estimates from actual projects, and the pluses are cost estimates. The funnel-shaped lines narrowing to the right represent Boehm’s sense of how our estimates get more accurate as we learn more about a project. Notice that when the specifics of the project are not yet known, the estimate can differ from the eventual actual cost by a factor of 4

## Slide 5: 3.3 Effort Estimation Sidebar 3.3 Causes of Inaccurate Estimates
Key causes
  Frequent request for change by users
  Overlooked tasks
  User's lack of understanding of the requirements
  Insufficient analysis when developing estimates
  Lack of coordination of system development, technical services, operations, data administration, and other functions during development
  Lack of an adequate method or guidelines for estimating

## Slide 6: 3.3 Effort Estimation Sidebar 3.3 Causes of Inaccurate Estimates (continued)
Key influences
  Complexity of the proposed application system
  Required integration with existing system
  Complexity of the program in the system
  Size of the system expressed as number of functions or programs
  Capabilities of the project team members
  Project team's experience with the application, the programming language, and hardware
  Capabilities of the project team members
  Database management system
  Number of project team member
  Extent of programming and documentation standards

## Slide 7: Software Project Estimation
Options for estimation
  Delay estimation until late in the project
    Attractive, but not practical
  Base estimates on similar projects that have already been completed
    Unfortunately, past experience has not always been a good indicator of future results
  Use relatively simple decomposition techniques to generate project cost and effort estimates
    “Divide and conquer” approach
  Use one or more empirical models for software cost and effort estimation
    Can be used as a cross-check for the previous option and vice versa

## Slide 8: Decomposition Techniques
Two different points of view for the decomposition approach
  Decomposition of the problem
  Decomposition of the process
But first, the project planner must
  Understand the scope of the s/w to be built
  Generate an estimate of its “size”

## Slide 9: Estimating Size
The accuracy of a s/w project estimate is predicated on a number of things:
  The degree to which the planner has properly estimated the size of the product to be built
  The ability to translate the size estimate into human effort, calendar time, and dollars (required availability of past records)
  The degree to which the project plan reflects the abilities of the s/w team
  The stability of product requirements and the environment that supports the s/w engineering effort

## Slide 10: Estimating Size
Sizing represents the project planner’s first major challenge
Size refers to a quantifiable outcome of the s/w project (e.g. LOC (Lines of Code) and/or FP(Function Points))

## Slide 11: Problem-Based Estimation of Size
Example of baseline productivity metrics are LOC/pm or FP/pm
Making the use of single baseline productivity metric is discouraged
In general, LOC/pm or FP/pm averages should be computed by project domain. Projects should be grouped by team size, application area, complexity, and other relevant parameters
Local domain averages should be used

## Slide 12: Problem-Based Estimation of Size
Statistical approach – three-point or expected-value estimate (Delphi’s Technique)
S = (sopt + 4sm + spess)/6
  S = expected-value for the estimation variable (size)
  sopt = optimistic value
  sm = most likely value
  spess = pessimistic value

## Slide 13: Problem-Based Estimation of Size
For example, the range of LOC estimates for the 3D geometric analysis function is optimistic, 4600 LOC; most likely, 6900 LOC; and pessimistic, 8600 LOC. Applying Equation, the expected value for the 3D geometric analysis function is 6800 LOC.
S = (sopt + 4sm + spess)/6
S = (4600 + 4 * 6900 + 8600)/6
S = 6800 LOC

## Slide 14: Problem-Based Estimation of Size
A review of historical data indicates that the organizational average productivity for systems of this type is 620 LOC/pm.
Based on a burdened labor rate of $8,000 per month, the cost per line of code is approximately $13. (8000/620 = 12.9)
Based on the LOC estimate and the historical productivity data, the total estimated project cost is $431,000. (33200*13 = 431600)
The estimated effort is 54 person-months. (33200/620=53.5)

## Slide 15: Introduction to Function Points
Can be used effectively as a means for measuring the functionality delivered by a system
Using historical data, function points can be used to
  Estimate the cost or effort required to design, code, and test the software
  Predict the number of errors that will be encountered during testing
  Forecast the number of components and/or the number of projected source code lines in the implemented system
Derived using an empirical relationship based on
  Countable (direct) measures of the software’s information domain
  Assessments of the software’s complexity
FP = count total * [0.65 + 0.01 * sum(Fi)]

## Slide 16: Introduction to Function Points
Information Domain Values
  Number of external inputs
  Number of external outputs
  Number of external inquiries
  Number of internal logical files
  Number of external interface files
Value Adjustment Factors (VAF)
  14 Factors

## Slide 17: Information Domain Values

## Slide 18: Information Domain Values
Number of external inputs
  Each external input originates from a user or is transmitted from another application
  They provide distinct application-oriented data or control information
  They are often used to update internal logical files
  They are not inquiries (those are counted under another category)
Number of external outputs
  Each external output is derived within the application and provides information to the user
  This refers to reports, screens, error messages, etc.
  Individual data items within a report or screen are not counted separately

## Slide 19: Information Domain Values
Number of external inquiries
  An external inquiry is defined as an online input that results in the generation of some immediate software response
  The response is in the form of an online output
Number of internal logical files
  Each internal logical file is a logical grouping of data that resides within the application’s boundary and is maintained via external inputs
Number of external interface files
  Each external interface file is a logical grouping of data that resides external to the application but provides data that may be of use to the application

## Slide 20: Value Adjustment Factors
Does the system require reliable backup and recovery?
Are specialized data communications required to transfer information to or from the application?
Are there distributed processing functions?
Is performance critical?
Will the system run in an existing, heavily utilized operational environment?
Does the system require on-line data entry?
Does the on-line data entry require the input transaction to be built over multiple screens or operations?

## Slide 21: Value Adjustment Factors
Are the internal logical files updated on-line?
Are the inputs, outputs, files, or inquiries complex?
Is the internal processing complex?
Is the code designed to be reusable?
Are conversion and installation included in the design?
Is the system designed for multiple installations in different organizations?
Is the application designed to facilitate change and for ease of use by the user?

## Slide 22: Function Point Computation
Identify/collect the information domain values
Complete the table shown below to get the count total
  Associate a weighting factor (i.e., complexity value) with each count based on criteria established by the software development organization
Evaluate and sum up the adjustment factors (see example in the next few slides)
  “Fi” refers to 14 value adjustment factors, with each ranging in value from 0 (not important) to 5 (absolutely essential)
Compute the number of function points (FP) FP = count total * [0.65 + 0.01 * sum(Fi)]
Information Weighting Factor
Domain Value Count Simple Average Complex
External Inputs _____ x 3 4 6 = _____
External Outputs _____ x 4 5 7 = _____
External Inquiries _____ x 3 4 6 = _____
Internal Logical Files _____ x 7 10 15 = _____
External Interface Files _____ x 5 7 10 = _____ Count total ________

## Slide 23: Function Point Example
FP = count total * [0.65 + 0.01 * sum(Fi)]
FP = 50 * [0.65 + (0.01 * 46)]
FP = 55.5 (rounded up to 56)
Information Weighting Factor
Domain Value Count Simple Average Complex
External Inputs 3 x 3 4 6 = 9
External Outputs 2 x 4 5 7 = 8
External Inquiries 2 x 3 4 6 = 6
Internal Logical Files 1 x 7 10 15 = 7
External Interface Files 4 x 5 7 10 = 20 Count total 50

## Slide 24: An Example of FP-Based Estimation

## Slide 25: An Example of FP-Based Estimation
For the purpose of this estimate, the complexity weighting factor is assumed to be average

## Slide 26: An Example of FP-Based Estimation
Value Adjustment Factors
52

## Slide 27: An Example of FP-Based Estimation
Now,
  FPestimated = count_total  [0.65 + 0.01   (Fi)]
    Fi (i = 1 to 14 are value adjustment factors)
So,
  FPestimated = 320  [0.65 + 0.01  52] = 375 (approx.)
Let,
  Average Productivity = 6.5 FP/pm
  Labor rate = $8,000 per month
So,
  Cost per FP = Labor Rate/Average Productivity = $1,230 (approx.)
  Total estimated project cost = FPestimated * Cost per FP = $461,000 (approx.)
  Estimated effort = FPestimated / Average Productivity = 58 person-months (approx)

## Slide 28: An Example
password, panic button, activate/deactivate
zone inquiry, sensor inquiry
system configuration file
messages, sensor status
test sensor, zone setting, alarm alert, a/d
Let ΣFi = 46
Size in FP?
Effort?
Cost?

## Slide 29: Estimating Size
A hierarchy of estimation models
Address the following areas
  Application composition model
  Early design stage model
  Post-architecture stage model
Three different sizing options are available
  Application points
  Function points
  Lines of source code

## Slide 30: Effort Estimation COCOMO (Constructive Cost Model)
Introduced by Boehm
COCOMO I
  effort as a function of size
COCOMO II
  updated version
  effort as a function of size
  Includes cost factors as a multiplier
  include models of reuse
  requires sizing information like all other models

## Slide 31: Effort Estimation COCOMO I
Effort (E) = a (KLOC)b person_months
Development Time (D) = c x E d months
Organic: small teams, rigid requirements
Semi detached: medium teams, less rigid requirements
Embedded: combination of O and S (h/w, s/w,…)

## Slide 32: An Example
E?
D?

## Slide 33: An Example
KLOC = 33200/1000 = 33.2
E = 2.4*(33.2)^1.05 = 94.9 = (approx. 95 p-m)
D = 2.5*(94.9)^0.38 = 14.10 = (approx. 14 months)

## Slide 34: An Example
KLOC = 33200/1000 = 33.2
E = 2.4*(33.2)^1.05 = 94.9 = (approx. 95 p-m)
D = 2.5*(94.9)^0.38 = 14.10 = (approx. 14 months)
Person Estimation = N = E/D = 95/14 = (approx. 7 person)
Productivity = P = KLOC/E = 33.2/95 = 0.34 KLOC/PM

## Slide 35: Effort Estimation COCOMO II: Stages of Development
Application composition
  prototyping to resolve high-risk user interface issues
  size estimates in application/object points
Early design
  to explore alternative architectures and concepts
  size estimates in function points
Post architecture
  development has begun
  size estimates in lines of code

## Slide 36: Estimating Size
Application points are computed using counts of the number of
  Screens (at the user interface)
  Reports
  Components likely to be required to build the application

## Slide 37: Estimating Size
Complexity weights for object types

## Slide 38: Estimating Size
Determine Object Points: Add all weighted object instances to get object point count

## Slide 39: Estimating Size
Determine object points based on reuse of code
New Object Points (NOP) =
NOP differ from the object point count because there may be reuse

## Slide 40: Estimating Size
Productivity rate for object points

## Slide 41: Estimating Size
Effort in PM =

## Slide 42: Cocomo-II Example
Use Cocomo-II model to estimate effort required to build an Order Taking system for restaurant that produces 15 screens, 6 reports and will require 70% new software components. Assume average complexity and average developer/environment maturity.
Object | Count | Complexity | Weight Factor | Total Objects
Screen | 15 | Medium | 2 | 30
Report | 6 | Medium | 5 | 30
Components | 0 | NA | NA | 0
Total Object Points: |  |  |  | 60

## Slide 43: Cocomo-II Example
It is mentioned that 70% new software components will be developed. So, the remaining 30% can be reused.
New Object Points (NOP) =
NOP =
NOP =
NOP = 42

## Slide 44: Cocomo-II Example
Since developer/environment maturity is average, productivity (PROD) = 13
Effort =
Effort =
Effort = 3.23 person months

## Slide 45: References
Shari PFleeger, Joanne Atlee, Software Engineering: Theory and Practice, 4th Edition
Roger S. Pressman, Software Engineering A Practitioner’s Approach, 9th Edition. McGrawHill